## Sheet1
|  | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12
A.K. | Evaluation Plan Development | [12 empty] | 35693 | bar: Q1
F.P/S.D. | LANCE implementation of User Interface | bar: Q1
F.P. | Completion and Testing of Flood "blob" Detection Algorithm in NEPFAS | bar: Q1
C.G. | Select and Process Sentinel-1 data to produce surface water maps for ANFIS training | bar: Q1 to Q2
F.P. | Completion and Testing of on-the-fly Anomaly Detection Code in NEPFAS | bar: Q2
C.G. | Train and Test ANFIS System | bar: Q2 to Q4
F.P/S.D. | LANCE integration of ANFIS in MODIS Flood Mapping System | bar: Q4 to Q5
F.P/S.D. | LANCE resuse of existing cloud, terrain shadow, and surface water masks and associated code to complete processing system for flood maps | bar: Q6
F.P/S.D. | LANCE processing of historical data for anomaly determination and for evaluation | bar: Q6 to Q7
C.G. | Evaluation of LANCE "alpha" flood map product | bar: Q6 to Q8
F.P/S.D. | LANCE integration of NEPFAS code for flood "blob" detection, population density thresholding, statistics calculations from the historical data, anomaly detection, and flood minimum size thresholding - components of potential flood detection | bar: Q7 to Q8
F.P. | Evaluation of LANCE Potential Flood Alert "alpha" Product | bar: Q8 to Q9
B.B. | Community Evaluation of LANCE flood map "beta" Product, culminating in start of production of flood map version 1 | bar: Q8 to Q10
F.P/S.D. | LANCE integration and testing of User Interface and potential flood detection algorithm implemented above | bar: Q9
B.B. | Community Evaluation of Potential Flood Alert "Beta" Product , cluminating in start of production of potential flood alert version 1 | bar: Q10 to Q11
F.P. | Update LANCE Flood Mapping System User Guide, Publication of Project Results | bar: Q10 to Q11
F.P | Project Float | bar: Q12
| sept | dec | mar | june | sept | dec | mar | june | sept | dec | mar | june
| 2021 |  |  |  | 2022 |  |  |  | 2023
228571.4286
AQUA (2002 -
Terra (1999 -